## Sheet1
BridgeLight Logframe and Finance AR1 Export
File name | BridgeLight_Logframe_and_Finance_AR1_export_2025-10-03.xlsx
Worksheet | AR1_OutputScore_DRAFT_do_not_overwrite
Cell A2 note | Review period shown as 01-Oct-24 to 30-Sep-25 because this is how partner reports were submitted. FCDO letter says 15-Oct to 14-Oct but finance has not recut yet.
Output | Impact weighting | Risk rating | Indicator ID | Indicator text | Baseline | Year 1 target | Endline target | Actual achieved value | Proposed output score | Evidence source | Variance explanation | Female 6-11 | Female 12-17 | Female 18-24 | Male 6-11 | Male 12-17 | Male 18-24 | Disability count | Ultra-poor HH count | Previously married / early union count | Forecast cost Year 1 GBP | Actual cost Year 1 GBP | Finance note
Output 1 Girls re-enter and remain in education | 35% | Medium | OP1.1 | Number of out-of-school or at-risk girls re-enrolled or newly retained through support package | 0 | 650 | 1200 | 684 | A | School registers; re-entry club forms; district validation sample | Above milestone. Some double-count risk removed in September cleaning. | 58 | 590 | 33 | 0 | 0 | 0 | 41 | 502 | 76 | 162000 | 174850 | Transport costs higher due to lake-shore schools
Output 1 Girls re-enter and remain in education | 35% | Medium | OP1.2 | Number of supported girls attending at least 80% of school days in last completed term | 0 | 500 | 900 | 472 | B | Term 3 attendance registers from 36 schools | Under milestone due to late register submission from four schools. | 39 | 410 | 22 | 0 | 0 | 0 | 27 | 350 | 49 | 94000 | 98740 | Staff time loaded here, may belong in Output 4
Output 1 Girls re-enter and remain in education | 35% | Medium | OP1.3 | Number of girls completing at least 20 remedial learning sessions | 0 | 420 | 850 | 438 | A | Remedial class attendance sheets | Slightly above milestone. | 35 | 382 | 21 | 0 | 0 | 0 | 24 | 319 | 38 | 88000 | 81330 | Teacher stipends lower than forecast
Output 2 Schools provide safer WASH and safeguarding conditions for girls | 25% | Medium | OP2.1 | Number of separate, lockable girls latrine stances rehabilitated or newly functional | 6 | 24 | 40 | 31 | A | WASH engineer completion certificates; school verification photos | Above milestone, but four units still need disposal bins. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121000 | 148900 | Cement and transport over budget
Output 2 Schools provide safer WASH and safeguarding conditions for girls | 25% | Medium | OP2.2 | Number of schools with menstrual health supplies and trained focal teachers | 0 | 20 | 40 | 17 | C | Training attendance sheets; supply distribution records | Below milestone because three schools had no female focal teacher available. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 39600 | Supplies procured late
Output 3 Households reduce immediate cost barriers to girls attendance | 25% | High | OP3.1 | Number of caregivers receiving education hardship grant linked to girls attendance plan | 0 | 400 | 800 | 392 | B | Mobile money payment list; school attendance follow-up sample | Slightly below target after deduplication of 16 caregiver records. | 0 | 0 | 0 | 96 | 118 | 178 | 12 | 392 | 0 | 146000 | 151440 | Payment fees higher than forecast
Output 3 Households reduce immediate cost barriers to girls attendance | 25% | High | OP3.2 | Number of girls receiving school re-entry kit or learning materials package | 0 | 550 | 1100 | 571 | A | Kit distribution forms; headteacher confirmations | Above milestone. | 48 | 498 | 25 | 0 | 0 | 0 | 33 | 421 | 64 | 103000 | 109250 | Extra notebooks bought locally
Output 3 Households reduce immediate cost barriers to girls attendance | 25% | High | OP3.3 | % of hardship grant households with verified attendance follow-up within 45 days | 0% | 75% | 85% | 68% | C | Follow-up tracker; district officer sample | Below milestone because September follow-ups incomplete. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 31000 | 24980 | Underspend due to vacant M&E assistant post
Output 4 District education actors use evidence to improve girls re-entry practice | 15% | Low | OP4.1 | Number of district learning meetings held with documented action points | 0 | 4 | 8 | 3 | B | Meeting minutes; attendance sheets | One meeting cancelled during district exam period. | 0 | 0 | 0 | 12 | 18 | 9 | 0 | 0 | 0 | 39000 | 32700 | Venue costs lower
Output 4 District education actors use evidence to improve girls re-entry practice | 15% | Low | OP4.3 | Number of school/community actors trained on girls re-entry and safeguarding protocols | 0 | 120 | 240 | 136 | A | Training attendance sheets; pre/post quiz forms | Above target. | 0 | 64 | 8 | 28 | 31 | 5 | 5 | 0 | 0 | 54000 | 58630 | Facilitator travel higher
TOTAL | 100% | [10 empty] | 180 | 1944 | 109 | 136 | 167 | 192 | 142 | 2376 | 291 | 880000 | 920420 | Forecast is AR1 only, not full life-of-project