Warm Welcome Monitoring and Spend Table

NLCF progress update source table

| File name | WarmWelcome_monitoring_budget_tracker_April2026.xlsx |
| --- | --- |
| Worksheet | Update for Lottery maybe |

| Section for NLCF update | Indicator / cost heading | Original target / budget | Actual / spend to 30 Apr 2026 | Evidence or note | Children 8-11 | Young people 12-16 | Adults 17-64 | Older residents 65+ | Female | Male | Non-binary / not said | Vulnerability / low-income flag |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project story | Number of hub sessions delivered | 96 | 88 | Tuesday sessions paused during boiler repair in January |  |  |  |  |  |  |  |  |
| Difference made | Unique people attending at least one hub session | 120 | 148 | Sign-in sheets, some names duplicated where children used nicknames | 42 | 39 | 53 | 11 | 86 | 54 | 5 | 97 |
| Difference made | Children and young people attending at least three sessions | 55 | 61 | Attendance tracker | 28 | 33 | 0 | 0 | 35 | 24 | 2 | 41 |
| Difference made | Community volunteers recruited and supported | 18 | 14 | Volunteer list; excludes people who only helped with cooking twice | 0 | 2 | 9 | 3 | 9 | 5 | 0 | 5 |
| Difference made | Participants reporting they feel less isolated | 65% | 58% | Only 38 feedback cards returned; informal chats much more positive | 0 | 8 | 25 | 5 | 23 | 12 | 3 | 29 |
| Difference made | Young people helping choose or lead activities | 24 | 27 | Youth board notes and activity sheets | 6 | 21 | 0 | 0 | 14 | 11 | 2 | 18 |
| Community involvement | Partner or local collaboration examples | 3 | 5 | School, food pantry, GP link worker, tenants group, local mosque |  |  |  |  |  |  |  |  |
| Learning | What worked | n/a | Food-first format worked best | Staff notes, volunteer meeting March 2026 |  |  |  |  |  |  |  |  |
| Learning | What did not work | n/a | Formal wellbeing survey had low response | Staff notes |  |  |  |  |  |  |  |  |
| Spend summary | Part-time project coordinator | £31,200 | £29,950 | Coordinator started three weeks late |  |  |  |  |  |  |  |  |
| Spend summary | Sessional youth workers | £13,600 | £16,480 | Extra cover needed during school holidays |  |  |  |  |  |  |  |  |
| Spend summary | Volunteer training and DBS checks | £4,200 | £3,140 | Fewer formal volunteers than planned |  |  |  |  |  |  |  |  |
| Spend summary | Food, heating and room costs | £13,500 | £16,260 | Winter heating higher; food prices increased |  |  |  |  |  |  |  |  |
| Spend summary | Activity materials and local trips | £8,000 | £7,850 | Mostly on local activities |  |  |  |  |  |  |  |  |
| Spend summary | Evaluation and admin | £8,000 | £4,780 | External evaluator not used yet |  |  |  |  |  |  |  |  |
| Spend summary | TOTAL | £78,500 | £78,460 | Finance lead says “basically fully spent”, but award letter says £82k |  |  |  |  |  |  |  |  |