ANSWER KEY - DO NOT INCLUDE IN DOCUMENTS

NLCF planted inconsistencies and grading sheet

| Issue type | Conflict / planted problem | Documents involved | True / intended value | What engine should catch |
| --- | --- | --- | --- | --- |
| Grant amount mismatch | Proposal and spreadsheet use £78,500; award letter says £82,000. | Document 1 + Document 3 vs Document 2 | £82,000 official NLCF award amount. | Spend summary should flag that tracker does not account for full awarded amount. |
| Spend variance issue | Spreadsheet shows total budget £78,500 and actual spend £78,460, implying £40 underspend, but against award letter value £82,000 the unaccounted balance is £3,540. | Document 2 vs Document 3 | Official remaining/unexplained amount is £3,540 unless budget change was approved. | Budget-vs-actual section should ask whether £3,500 was removed, reallocated or unspent. |
| Missing evidence indicator | Proposal promises 20 parent/carer feedback examples, but monitoring table has no row for parent/carer feedback examples collected. | Document 1 vs Document 3 | Missing data; intended target 20 comments. | Gap agent should request feedback examples or confirm unavailable. |
| Lower-than-target outcome | Proposal target says 65% participants feel less isolated; spreadsheet actual is 58%. This is not a contradiction, but it is a negative variance requiring learning narrative. | Document 1 vs Document 3 | Actual 58%. | Difference-made and learning sections should not overclaim success. |
| Beneficiary count arithmetic mismatch | Spreadsheet actual unique attendees is 148, but age disaggregation sums to 145: 42 + 39 + 53 + 11. Gender disaggregation also sums to 145: 86 + 54 + 5. | Document 3 internal | True total intended 148, with 3 people missing from disaggregation. | Numeric checker should flag incomplete disaggregation. |
| Date/reporting-period clarity | Award letter says first progress update covers 1 May 2025-30 April 2026. Spreadsheet says to 30 Apr 2026 but does not show the start date; proposal is application dated March 2025 and not a reporting period source. | Document 2 vs Document 3 | 1 May 2025-30 April 2026. | Extractor should source period from award letter, not infer from file date/application date. |
| Awkward formatting / messy reality | Proposal uses £78,500, £78.5k, and about eighty thousand; award letter uses exact £82,000. | Document 1 vs Document 2 | Official award £82,000. | Money parser should normalise formats and prefer award letter for contractual amount. |