# (2) SOURCE INPUT BUNDLE

## Synthetic test material notice

This source bundle is fictional and deliberately realistic. It includes minor messiness, inconsistent date formats, small reconciliation issues, and information spread across multiple source items. It is internally reconcilable to the Golden Annual Review.

## SOURCE ITEM 1 — Winning Proposal Extract

Document title: Safe Schools, Strong Futures — Final Technical Proposal
Lead applicant: CedarBridge International — fictional UK-registered INGO
Local partners: Kalo Learning Network; Amara Water and Sanitation Trust — fictional
Submitted to: FCDO Nambara Education and Inclusion Window — fictional
Submission date: 18 January 2024
Programme period proposed: 1 April 2024 to 31 March 2028
Total requested budget: £3,180,000

### 1.1 Programme summary

Safe Schools, Strong Futures will support 40 rural schools in Lake Kalo and North Karu regions of Nambara to improve girls’ attendance, safety, dignity, and participation. The programme will combine school WASH rehabilitation, menstrual health support, girls’ clubs, safeguarding training, referral systems, and community accountability.

### 1.2 Theory of change

If schools have safe and sex-segregated WASH facilities, girls receive menstrual health support, teachers and safeguarding focal points apply safe-school procedures, and caregivers monitor safety and attendance, then girls aged 10–18 will attend school more regularly and learn in safer, more inclusive school environments.

This theory depends on four assumptions:

- School leadership will allow girls’ clubs and safeguarding focal points to operate.

- Families will support adolescent girls’ regular attendance when school safety and dignity improve.

- Local authorities will maintain referral pathways for child protection concerns.

- Water access improvements remain functional through the dry season.

### 1.3 Impact statement

Girls in rural Nambara complete basic education with improved health, safety, and confidence.

### 1.4 Outcome statement

Girls aged 10–18 in 40 target rural schools attend regularly and learn in safer, more inclusive school environments.

### 1.5 Logframe extract

| Level | Indicator | Baseline | Year 1 milestone | Year 2 target | Year 3 target | Endline target | Means of verification |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome | OC1. % of enrolled girls aged 10–18 attending at least 80% of school days in term reviewed | 58% | 62% | 68% | 72% | 78% | School attendance registers; termly MEL audit |
| Outcome | OC2. % of target schools meeting programme minimum safe WASH and safeguarding standard | 12% | 25% | 50% | 70% | 85% | School spot checks; safeguarding verification checklist |
| Outcome | OC3. % of surveyed caregivers reporting confidence that target schools are safe for adolescent girls | 41% | 50% | 60% | 68% | 75% | Annual caregiver survey |
| Output 1 | 1.1 Number of target schools with completed sex-segregated latrine rehabilitation and water access improvements | 0 | 18 | 40 | 40 | 40 | Engineer completion certificates; site photos |
| Output 1 | 1.2 % of installed handwashing stations functional at spot check | 0% | 70% | 80% | 85% | 90% | Spot-check report |
| Output 1 | 1.3 Number of school WASH operation and maintenance committees active | 0 | 18 | 40 | 40 | 40 | Committee minutes; attendance sheets |
| Output 2 | 2.1 Number of girls receiving menstrual health sessions and dignity kits | 0 | 7,200 | 14,400 | 18,000 | 22,000 | Distribution registers; session attendance sheets |
| Output 2 | 2.2 Number of trained girls’ club mentors active | 0 | 82 | 160 | 190 | 220 | Training records; club monitoring forms |
| Output 2 | 2.3 Average self-reported menstruation-related absence days per term among sampled girls | 4.8 | 3.9 | 3.2 | 2.7 | 2.2 | Girls’ club survey |
| Output 3 | 3.1 Number of teachers and safeguarding focal points trained | 0 | 205 | 420 | 520 | 620 | Training attendance sheets |
| Output 3 | 3.2 Number of schools using referral and case-log tools correctly | 0 | 19 | 40 | 40 | 40 | Safeguarding supervision checklist |
| Output 3 | 3.3 % of recorded child-protection referral cases closed or escalated within 30 days | 0% | 65% | 80% | 85% | 90% | Referral logs; partner case review |
| Output 4 | 4.1 Number of parent and community dialogue sessions held | 0 | 72 | 160 | 220 | 280 | Activity logs; attendance sheets |
| Output 4 | 4.2 Number of caregivers participating in confidence and safety feedback surveys | 0 | 2,360 | 4,800 | 5,200 | 5,500 | Survey dataset |
| Output 4 | 4.3 Number of schools with updated school improvement plans including girls’ safety and attendance actions | 0 | 18 | 40 | 40 | 40 | School improvement plans |

### 1.6 Output weightings and risk at approval

| Output | Weighting | Risk at approval |
| --- | --- | --- |
| Output 1. School WASH infrastructure rehabilitated and maintained | 30% | Medium |
| Output 2. Girls receive menstrual health support and peer-led school club services | 25% | Low |
| Output 3. Teachers and school safeguarding focal points apply safe-school procedures | 25% | Medium |
| Output 4. Communities and school committees monitor girls’ safety and attendance | 20% | Low |

## SOURCE ITEM 2 — Grant Agreement / MoU Extract

Document title: Accountable Grant Arrangement — Safe Schools, Strong Futures
Parties: FCDO Nambara Education Team and CedarBridge International
Reference: FIC-NAM-EDU-0447
Signed: 25/03/2024
Effective date: 01-Apr-2024
End date: 31 March 2028
Total maximum contribution: £3,180,000

### 2.1 Payment and reporting

- The grant will support four programme years from 1 April 2024 to 31 March 2028.

- Annual financial and narrative reports are due within 45 calendar days of each programme year end.

- The Year 2 Annual Review covers the period 01/04/2025 to 31/03/2026 and is due by 15 May 2026.

- Reports must include:

  - progress against logframe outcome and output indicators;

  - output scoring using the FCDO A++ to C scale;

  - explanation of underperformance where relevant;

  - value-for-money analysis;

  - updated risk assessment;

  - safeguarding and fraud reporting;

  - gender, age, disability, and vulnerability disaggregation where available;

  - management actions and recommendations for the next period.

### 2.2 Budget

| Budget heading | Total approved budget |
| --- | --- |
| Personnel and technical assistance | £820,000 |
| School WASH works and supplies | £1,060,000 |
| Training, girls’ clubs, and community engagement | £610,000 |
| Monitoring, evaluation, learning, and audit | £280,000 |
| Operations, travel, and security | £250,000 |
| Indirect costs | £160,000 |
| Total | £3,180,000 |

Year 2 approved budget: £870,000.

Budget virements above 10% of a major heading require prior written approval. No personal or identifiable child data should be included in published reports.

### 2.3 Conditions

- CedarBridge International remains accountable for partner delivery and financial reporting.

- SEAH allegations must be notified within 72 hours.

- Fraud, loss, or misuse of funds must be notified immediately.

- Assets purchased above £500 must be recorded on the asset register.

- All reporting should protect personal data and avoid identifying individual children.

## SOURCE ITEM 3 — Indicator Tracking Spreadsheet Rendered as Table

File name: SSSF_Y2_indicator_tracker_FINALish_v7.xlsx
Owner: CedarBridge International MEL team
Last edited: 12/05/26
Note in workbook tab: “Figures still to confirm with partners?? use HQ cleaned cols where duplicate notes exist.”

| Indicator | Baseline | Y1 milestone / actual | Y2 target | Actual this period | Means of verification | Notes / caveats |
| --- | --- | --- | --- | --- | --- | --- |
| OC1. % enrolled girls attending at least 80% of school days | 58% | 62% | 68% | 66% | School registers; MEL audit | Based on 37/40 schools. Three March registers missing or damaged. |
| OC2. % target schools meeting safe WASH + safeguarding minimum standard | 12% | 25% | 50% | 46% | Spot checks; safeguarding verification | 18/39 assessed schools. One verification visit cancelled. |
| OC3. % caregivers confident schools are safe for adolescent girls | 41% | 50% | 60% | 63% | Annual caregiver survey | n=5,126. Weighting not applied. |
| 1.1 Schools with completed latrine rehab + water access improvements | 0 | 18 | 40 | 38 | Engineer certificates; site photos | Two sites in final batch delayed. |
| 1.2 % handwashing stations functional at spot check | 0% | 70% | 80% | 76% | Spot-check report | 15 stations need repair or replacement water containers. |
| 1.3 School WASH O&M committees active | 0 | 18 | 40 | 39 | Committee minutes | One school committee not meeting regularly. |
| 2.1 Girls receiving menstrual health sessions and dignity kits | 0 | 7,200 | 14,400 | 15,230 | Distribution registers; session attendance | KLN narrative says 15,318; HQ cleaned duplicate entries from 3 schools. Use 15,230. |
| 2.2 Trained girls’ club mentors active | 0 | 82 | 160 | 172 | Mentor list; school club forms | 118 teacher mentors, 54 community mentors. |
| 2.3 Avg self-reported menstruation-related absence days/term | 4.8 | 3.9 | 3.2 | 3.0 | Girls’ club survey | Self-reported; sample = 1,120 girls. |
| 3.1 Teachers and safeguarding focal points trained | 0 | 205 | 420 | 391 | Training attendance sheets | Feb cascade round moved to May 2026. |
| 3.2 Schools using referral and case-log tools correctly | 0 | 19 | 40 | 34 | Supervision checklist | Six schools need monthly coaching. |
| 3.3 % referral cases closed or escalated within 30 days | 0% | 65% | 80% |  | Referral logs; partner case review | Spreadsheet blank. Partner narrative says 17 of 23 referrals closed/escalated in 30 days. |
| 4.1 Parent/community dialogue sessions held | 0 | 72 | 160 | 148 | Activity logs | Some combined during harvest period. |
| 4.2 Caregivers in confidence and safety feedback surveys | 0 | 2,360 | 4,800 | 5,126 | Survey dataset | 5,290 women and 3,170 men attended wider dialogues, not survey. |
| 4.3 Schools with updated school improvement plans | 0 | 18 | 40 | 40 | SIP files | All plans include girls’ safety and attendance action. |

### Disaggregation tab

| Category | Figure | Notes |
| --- | --- | --- |
| Girls directly reached | 15,230 | Cleaned unique count |
| Girls aged 10–14 | 10,920 | Age from school records |
| Girls aged 15–18 | 4,310 | Age from school records |
| Girls with reported disability | 812 | Washington Group short questions used in 31 schools only |
| Girls supported after recent re-entry to school | 1,184 | May overlap with disability count |
| Teachers/focal points trained | 391 | 236 female; 155 male |
| Caregivers surveyed | 5,126 | Survey respondents |
| Wider parent/community dialogue participants | 8,460 | 5,290 women; 3,170 men |

### Finance tab

| Financial item | Amount |
| --- | --- |
| Total grant value | £3,180,000 |
| Year 2 approved budget | £870,000 |
| Year 2 expenditure | £812,600 |
| Year 2 underspend | £57,400 |
| Year 1 expenditure | £668,900 |
| Cumulative expenditure to 31/03/2026 | £1,481,500 |
| Procurement saving on latrine materials | £21,800 |

## SOURCE ITEM 4 — Partner Narrative Notes / Field Updates

### 4.1 Kalo Learning Network informal update

Email subject: Y2 numbers and safeguarding bits — please clean before donor report
Date: 9 May 2026
From: Programme Coordinator, Kalo Learning Network
To: CedarBridge MEL Lead

We finished most of the girls’ sessions before schools closed. My team count is 15,318 girls, but I know the central sheet has 15,230 because some girls at three schools were entered twice. Use your cleaned figure if that is what finance and MEL want.

Mentors are at 172 active. Some are teacher mentors and some are community women mentors. Clubs are working best where the head teacher attends the first meeting.

Safeguarding is the harder bit. We trained 391 people. We planned 420, but the Feb round didn’t happen because schools closed and two trainers were not available. We moved that round to May 2026. Six schools are still weak on case logs. They use the forms after visits but not every week.

Referral cases: I counted 31 concerns logged. Of these, 23 needed referral/escalation. 17 were closed or escalated within 30 days. No SEAH report this year. Please don’t put child names in the report.

Attendance: 66% for girls attending 80%+ days. BUT only 37 schools have complete registers. Three March registers were wet/damaged or not signed properly. Direction is still good from my view.

### 4.2 Amara Water and Sanitation Trust field note

Document: AWST progress note, March 26
Author: Infrastructure Officer
Format: copied from WhatsApp notes into Word

38 schools completed. Two school sites not done by 31 Mar because road washed out and roofing sheets came late. Materials now at supplier yard. Works can finish in June if no more access issue.

Handwashing spot check: 76% working. Main reasons not working: broken tap heads, no water in containers, one stand loose. Not big construction problems.

39 WASH committees active. One committee exists but has not met since Dec 2025.

Procurement saved money this year. Bulk purchase reduced material cost by about £21,800 compared with budget estimate.

### 4.3 CedarBridge programme manager note

Document: Steering group note — 14/04/2026

Overall delivery feels good. Output 2 is clearly strongest. Output 3 needs management attention. We should not pretend safeguarding is fully embedded. It is not. Training numbers are close, but behaviour change in schools is slower.

Community confidence is better than expected. Caregiver survey came out at 63%, above the 60% target. Field staff think parents trust the programme more when they can see the latrines finished and girls’ clubs running.

Recommend for Y3:

- finish two WASH works by 30 June;

- run missed safeguarding training by end July;

- monthly coaching for six schools;

- include WASH accessibility checklist because disability evidence is thin;

- fix attendance register process.

## SOURCE ITEM 5 — Activity Log

File name: SSSF_activity_log_Y2_combined.xlsx
Notes: dates copied from partner sheets without reformatting.

| Date | Activity | Location label | Lead | Output link | Attendance / result |
| --- | --- | --- | --- | --- | --- |
| 05-Apr-25 | Year 2 workplan refresh workshop | Central programme office | CedarBridge | All outputs | 18 staff and partner reps |
| 18/04/2025 | First WASH batch verification | School cluster A | AWST | Output 1 | 11 schools checked |
| 02-May-2025 | Girls’ club mentor refresher | North training hub | KLN | Output 2 | 74 mentors |
| 21.05.25 | Parent dialogue meetings round 1 | Cluster schools | KLN | Output 4 | 38 meetings |
| 10-Jun-25 | Dignity kit distribution round 1 | 20 schools | KLN | Output 2 | 7,846 girls |
| 28/07/25 | Safeguarding focal point training | Central training venue | KLN | Output 3 | 126 participants |
| 13-Aug-2025 | WASH O&M committee coaching | 18 schools | AWST | Output 1 | 18 committees |
| 09/10/25 | Caregiver safety survey round | 40 schools | CedarBridge MEL | Output 4 / Outcome | 5,126 survey respondents |
| 12-Nov-2025 | Referral pathway supervision visit | School cluster C | KLN | Output 3 | 16 schools reviewed |
| 18.01.26 | Girls’ health sessions round 2 | All target schools | KLN | Output 2 | 7,472 girls |
| Feb 2026 | Planned safeguarding cascade training | Not completed | KLN | Output 3 | Postponed to May 2026 |
| 06-Mar-2026 | Final WASH spot check | 39 assessed schools | AWST | Output 1 / Outcome | 18 schools met full combined standard |
| 26/03/2026 | School improvement plan review | 40 schools | CedarBridge/KLN | Output 4 | 40 plans updated |

## SOURCE ITEM 6 — Photo Caption Evidence List

Folder name: Y2_photos_selected_for_evidence_no_faces
Note: all images synthetic; captions only. No real images or personal data.

| Photo ref | Caption | Linked evidence |
| --- | --- | --- |
| IMG_1042 | Newly completed girls’ latrine block at target school, photographed after engineer sign-off. No children visible. | Output 1.1 |
| IMG_1088 | Handwashing station with water container and soap outside classroom block. | Output 1.2 |
| IMG_1170 | WASH committee meeting notes pinned on school noticeboard, names blurred. | Output 1.3 |
| IMG_1265 | Girls’ club mentor refresher session; wide room shot, faces not identifiable. | Output 2.2 |
| IMG_1391 | Dignity kit boxes stacked before distribution; labels show programme code only. | Output 2.1 |
| IMG_1448 | Safeguarding referral pathway poster displayed in staff room. | Output 3.2 |
| IMG_1510 | Parent dialogue session with participants photographed from back of room. | Output 4.1 |
| IMG_1603 | School improvement plan page showing attendance and safety action lines; personal names cropped. | Output 4.3 |