BridgeLight Education Trust

Donor Report — Foreign, Commonwealth & Development Office

Reporting period: 2024-10-15 to 2025-10-14

FCDO Annual Review

6 June 2026

# A. Summary and Overview

## Annual Review Summary Sheet

The programme made steady progress during the Annual Review period from 15 October 2024 to 14 October 2025. Overall delivery remained on track against the agreed Outputs and Indicators.

# B. Performance and Conclusions

## Annual Outcome Assessment

Outcome delivery was assessed against the results framework. Girls demonstrated improved retention and attendance against milestone targets.

# C. Detailed Output Scoring

## Output scoring against logframe

Output scoring against the logframe is summarised below.

| Output | Indicator | Baseline | Milestone | Target | Actual | Score | Evidence |
| --- | --- | --- | --- | --- | --- | --- | --- |
| OP1.1 | Girls re-enrolled | 0 | 650 | 650 | 684 | A+ | School registers |
| OP2.1 | Latrine stances functional | 0 | 24 | 24 | 31 | A++ | Site verification |
| OP4.1 | District learning meetings | 0 | 3 | 3 | 3 | A | Meeting minutes |

# Evidence and Evaluation

## Evidence quality and gaps

Monitoring data were drawn from partner returns and spot checks. Limitations in late attendance registers were noted and managed.

# Risk rating / assumptions / controls, Assumptions and Safeguarding

## Risk rating / assumptions / controls update

Safeguarding controls remained active. Assumption on focal teacher availability was partially realised.

# D. Value for Money

## Value for Money measures

Economy and efficiency were acceptable relative to forecast. Effectiveness was supported by output delivery evidence.

# F. Programme Management: Delivery, Commercial and Financial Performance

## Delivery, commercial and financial performance

Year 1 spend was GBP 920,420 against a budget of GBP 880,000 with variances explained by accelerated delivery.

# Recommendations and Action Points

## Recommendations and action points

Complete menstrual health training in the three remaining schools before the next review period.

# Assumptions & Caveats

Teacher focal points remain in post for the review period.