Organisation

Donor Report — Foreign, Commonwealth & Development Office

Reporting period: 2025-04-01 to 2026-03-31

FCDO Annual Review

11 June 2026

# A. Summary and Overview

## Annual Review Summary Sheet

The programme impact objective was for girls to complete basic education in safer, more supportive learning environments.

The programme outcome objective was improved school retention, attendance, learning continuity, and reduced barriers.

684 girls were re-enrolled or newly retained against an AR1 logframe target of 650.

472 were recorded against a target of 500 for OP1.2.

438 were recorded against a target of 420 for OP1.3.

# B. Performance and Conclusions

## Annual Outcome Assessment

The programme impact objective was girls complete basic education in safer, more supportive learning environments.

The programme outcome objective was improved school retention, attendance, learning continuity, reduced barriers.

684 girls were re-enrolled or newly retained in AR1.

The AR1 logframe target for girls re-enrolled or newly retained was 650.

472 were recorded against OP1.2, compared with a target of 500.

438 were recorded against OP1.3, compared with a target of 420.

31 were recorded against OP2.1, compared with a target of 24.

# C. Detailed Output Scoring

## Output scoring against logframe

| Output | Impact weighting | Risk rating | Indicator | Baseline | Milestone | Actual | Score | Evidence | Explanation for variance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OP1.1 | not provided | not provided | not provided | not provided | not provided |  | not provided | not provided | not provided |
| OP1.2 | not provided | not provided | not provided | not provided | not provided |  | not provided | not provided | not provided |
| OP1.3 | not provided | not provided | not provided | not provided | not provided |  | not provided | not provided | not provided |
| OP2.1 | not provided | not provided | not provided | not provided | not provided |  | not provided | not provided | not provided |
| OP2.2 | not provided | not provided | not provided | not provided | not provided |  | not provided | not provided | not provided |
| OP2.3 | not provided | not provided | not provided | not provided | not provided | not provided | not provided | not provided | not provided |
| OP3.1 | not provided | not provided | not provided | not provided | not provided |  | not provided | not provided | not provided |
| OP3.2 | not provided | not provided | not provided | not provided | not provided |  | not provided | not provided | not provided |
| OP3.3 | not provided | not provided | not provided | not provided | not provided |  | not provided | not provided | not provided |
| OP4.1 | not provided | not provided | not provided | not provided | not provided |  | not provided | not provided | not provided |
| OP4.2 | not provided | not provided | not provided | not provided | not provided | not provided | not provided | not provided | not provided |
| OP4.3 | not provided | not provided | not provided | not provided | not provided |  | not provided | not provided | not provided |

# Evidence and Evaluation

## Evidence quality and gaps

The programme objective at impact level was girls complete basic education in safer, more supportive learning environments.

The outcome objective was improved school retention, attendance, learning continuity, reduced barriers.

684 girls were re-enrolled or newly retained against an AR1 logframe target of 650.

472 were recorded against a target of 500 for OP1.2.

438 were recorded against a target of 420 for OP1.3.

31 were recorded against a target of 24 for OP2.1.

# Risk rating / assumptions / controls, Assumptions and Safeguarding

## Risk rating / assumptions / controls update

FCDO required a risk and safeguarding update as part of the Annual Review pack.

The programme impact objective was girls complete basic education in safer, more supportive learning environments.

The programme outcome objective was improved school retention, attendance, learning continuity, reduced barriers.

OP1.1 reached 684 girls against an AR1 logframe target of 650.

OP1.2 recorded 472 against a target of 500.

# D. Value for Money

## Value for Money measures

# F. Programme Management: Delivery, Commercial and Financial Performance

## Delivery, commercial and financial performance

The programme aimed to support girls to complete basic education in safer, more supportive learning environments.

The intended outcome was improved school retention, attendance, learning continuity, and reduced barriers.

OP1.1 reached 684 girls re-enrolled or newly retained against an AR1 logframe target of 650.

OP1.2 recorded 472 against a target of 500.

# Recommendations and Action Points

## Recommendations and action points

The Annual Review requirement included Recommendations and action plan.

The first Annual Review period ran from 2024-10-15 to 2025-10-14.

OP1.1 reached 684 against an AR1 target of 650.

OP1.2 reached 472 against a target of 500.

OP1.3 reached 438 against a target of 420.

OP2.1 reached 31 against a target of 24.