## Sheet1
Status | Issue | Plain English meaning + what it blocks | Potential fix (minimal, contract-first)
Resolved | Export endpoint OpenAPI media type | OpenAPI now correctly says the export returns a DOCX binary, so frontend can implement download safely. C-2 no longer blocked on export. | No action. Keep as reference pattern for other endpoints’ OpenAPI typing.
Needs action (BLOCKER) | NGO Profile path prefix mismatch (/api/ngo-profile* vs /ngo-profile*) | Frontend/docs call /api/ngo-profile but runtime only exposes /ngo-profile. Blocks profile gate + completeness checks (B-1/B-2) and anything that needs profile status (D-1). | Pick one canonical prefix and align backend routes + OpenAPI + docs. Fastest: add /api prefix aliases (or move router under /api) and keep old paths only if needed.
Needs action (BLOCKER) | Missing list endpoints (GET /api/fit-scans, GET /api/proposals) | Dashboard needs “Recent Fit Scans” and “My Proposals”. Those list endpoints don’t exist in OpenAPI. Blocks D-1 Dashboard. | Implement GET list endpoints (paginated, newest first) + document in both API_CONTRACT files + add OpenAPI response models.
Needs action (HIGH) | Auth success response schemas are {} in OpenAPI (exchange, magic-link/consume, refresh) | Runtime may work, but OpenAPI is untyped → contract-first frontend tooling will keep stopping or relying on any. Risks A-phase auth flows and future audits. | Add explicit response_model (token payload) for those endpoints; ensure OpenAPI shows access_token, refresh_token, token_type, expires_in (+ optional user).
Needs action (HIGH) | No contract-backed opportunity title source | Fit scans/proposals only have funding_opportunity_id; no title field and no opportunity detail endpoint. Blocks clean UX on fit-scan results, proposal generation summary, proposal viewer header, and dashboard list readability. | Minimal: add opportunity_title to FitScanResponse + ProposalResponse/ProposalDetailResponse via DB join. Alternative: add GET /api/funding-opportunities/{id} with {id,title}.
Needs action (BLOCKER) | content_json schema opaque | Proposal viewer (C-2) needs deterministic section rendering/statuses. OpenAPI says content_json is arbitrary object. Blocks C-2 viewer implementation without guessing. | Define a typed schema for content_json (sections array with key/title/status/content/assumptions/evidence_used) and publish it in OpenAPI + API_CONTRACT.
Needs action (MEDIUM) | Regenerate contract mismatch (docs mention {section}; OpenAPI is path-only) | Frontend can’t implement per-section regen as spec implies. Blocks “regen UX polish” (not basic regen if you accept full-proposal regen). | Decide: full-proposal regen only (update specs/docs), or support per-section regen (add request body + behavior + update OpenAPI).
Needs action (MEDIUM) | OpenAPI missing Bearer securitySchemes + operation security | API is protected in practice, but OpenAPI doesn’t declare it. Breaks codegen + contract-readiness checks; increases integration risk. | Add components.securitySchemes (HTTP bearer) + apply security to protected endpoints (global or per-route).
Needs action (HIGH) | Error envelope mismatch / incomplete error schemas across endpoints | Contracts expect a standard envelope; OpenAPI still shows FastAPI HTTPValidationError and omits many 401/403/404/429/500 schemas. Causes repeated STOPs and inconsistent frontend error handling. | Standardize: define one StandardErrorResponse model and add it to all protected endpoints’ 4xx/5xx responses in OpenAPI; align docs.
Needs action (HIGH) | Billing schemas incomplete (checkout untyped request; portal {} response) | Billing UI (E-1) can’t be built contract-first. Blocks E-1 or forces unsafe assumptions. | Add typed request/response models: checkout `{plan: "GROWTH"
Needs action (MEDIUM) | Google callback documented as redirect, OpenAPI shows JSON 200 {} | OAuth callback semantics unclear in schema. Risks A-phase Google login correctness and future tooling. | Update OpenAPI to represent 3xx redirect (+ Location header), not 200 JSON; keep errors as JSON envelope.